## GANTT Chart
Description | Responsibility | Due Date | 2008-09-19 | 2008-09-22 | 2008-09-23 | 2008-09-24 | 2008-09-25
Venue
Research venues
Compare venue prices
Send suggestions to Manager to narrow down options
Visit Manager's selected venue/s
Check if other events are on same dates - for staff and at venue
Ensure there is adequate mobile phone coverage and network access in rooms
Approval requested from Manager
Request ITG team support
Deposit paid for venue booking
Costs included on budget spreadsheet
Take ITG on site visit to check equipment set up requirements
Invitations
Confirm conference theme
Confirm guest list
Design save the date invitations
Request assistance from Web developers
Approval requested from Manager
Send out save the date invitations
Design formal invitations (remember to include dress code, maps, info sheets, room sharing option excl. Eds and dietary requirements)
Request assistance from Web developers
Approval requested from Manager
Send out formal invitations to internal guests
Send out formal invitations to external guests
Follow up all outstanding RSVPs
Double check all attendees, room allocations, dietary requirements etc
Conference Presentations
Ensure the conference venue has round tables to allow people to move freely between tables - large conference room - 100 pax
Confirm presenters
Design presentation template (to fit theme)
Send out template to presenters
Finalise agenda
Approval requested from Manager
Send final agenda to BD to add to delegates packs
Send reminder email to presenters to review presentations
Create panel slides and save with timings into worksite
Update timings to pres sign off sheet
Send reminder email to presenters for final version of presentations
Send presentations to BD for formatting
Save presentations on show laptops and on usb sticks/disc in chronological order for ease of retrieval
Send panellists their list of questions in advance
Secretariat - ITG Support
Ensure there are at least 3 rooms at the venue - one for the Secretariat with at least 10 connections for network access - approx 12 pax total, plus two rooms for conference calls and/or client meetings
Request support from ITG team
Check number of laptops/network lines required
Check other equipment to be hired - printers/faxes etc
Email team to check current project requirements
Accommodation
Create rooming list for staff sharing or staying in single rooms
Ensure all EDs and guest speakers have their own room
Approval requested from Manager
Group Activities
Research different activities
Compare activity prices
Organise decorations (eg balloons, flowers, wine, banners etc)
Book activities
Check whether there are any particular activities to be undertaken this year (eg Wine Tasting/Karaoke - anything promised previously?)
Approval requested from Manager
Deposit paid
Names & details added to key contact list
Costs included on budget spreadsheet
Meals
Research meal options & menu selections
Compare meal prices
Approval requested from Manager
Costs included on budget spreadsheet
Check dietary requirements (add reminder to invitation)
Draft seating charts & request approval from Manager
Check who will be making speeches at dinner/s
Print final version of seating charts & name plates
Organise pre-dinner drinks for staff on arrival
Transport/Transfers
Ask EAs to book flights (check policy)
Research cost of buses and/or taxis to pick up from airport/office and return - check start time of Half Yearly Conference
Compare bus company prices
Deposit paid
Names & details added to key contact list
Costs included on budget spreadsheet
Staff informed of transportation arrangements
Double check details have copied across to the transport spreadsheet
Reconfirm all bookings
Special Requests/Other Considerations
Organise song for conference
Book car for Steve Waugh
EA cover arranged in the offices
Remind EAs and ask Execs to turn on out of office messages and/or divert phones to mobiles/let clients know they are at an offsite conference for 2 days
Things to do at conference
Names & details added to key contact list
Check presentations set up, microphones work, network access
Provide welcome packs at reception
Arrange pre-check in forms to speed up process
Ensure guest speakers are welcomed
Check all presentations are set up and working
Welcome staff to dinner and assist with seating charts
Act as liaison with restaurant/hotel staff for any problems
Ensure Secretariat is set up effectively
Things to take
IPod
Pens
Highlighters
Notepads
Reams of paper
Cabcharge books?
Conference folder
Gift wrap for presents?
Name tags, table plans, table cards
Copies of questionnaires for panel members
iPass log-in information sheets
Blank name-tags
A-K and L-Z signs for registration desk
Camera & Batteries
Football
Copies of full agenda
Key Contacts

## Key Contacts
Name | Company | Position/Comment | Phone | Mobile | Fax | Email

## Event Run Sheet
Tuesday 23 September 2008
Time | Task | Responsibility |  | Location | Key Contact | Contact Number
1200 | Go to Swiss Grand, Kath needs to remember to take: | Kath | Leanne
A-K and L-Z signs for registration desk
Blank name-tags
Camera & Batteries
CD with Conference Song
Conference folder
Copies of questionnaires for panel members
Event folder & checklists
Football
Gift wrap for presents
Info pack lanyards & spare name tags
iPass log-in information sheets
IPod & charger
Name plates & reserved seating plates for dinner, table plans, table cards
Poster & double sided tape
Murder Mystery Night character notes
Reams of paper
Stationery (envelopes, pens, highlighters, notepads etc)
Any staff arriving before 1500 must speak to Reception if early check in required
1300 | Set up registration desk, remember to give each delegate: | Kath | Leanne | The Lobby
* | Welcome/Information Pack on Lanyard
* | Room Key
* | Advise to see registration on check-out if need to pay anything on personal account (please note shared rooms have only 1 credit card listed on the hotel's records)
* | Character notes for Murder Mystery Night
* | Hotel check-in card to be signed
* | Speakers & panellists to be given final copy of agenda, questionnaires (if on a panel) and reminded to see Bernadette to sign-off a presentation (if they have done one)
1500 | Set up decorations for dinner |  |  |  | Anthea | TBC
1500 | Registration desk to open |  |  |  | Sara | 02 9365 9707
1600 | Set up secretariat. Check phone numbers provided on key contacts are working |  |  |  | James | 0406 400 717
1600 | Check in Melbourne staff
1700 | Coach departs Martin Place with Sydney staff
1730 | Check set up of dinner, name charts & table plan |  |  |  | Kath | 0410 174 814
1745 | Check in Sydney staff |  |  |  | Margarita
Dinner Timing Schedule
1830 | Pre-dinner drinks and canapes
1925 | Make announcement: "guests to be seated"
1930 | Welcome speech
1945 | Wine tasting competition
2000 | Buffet to open
2045 | Steve Waugh's speech
2115 | Dessert buffet to open, 2nd wine tasting competition
Wednesday 24 September 2008
Time | Task | Responsibility |  | Location | Key Contact | Contact Number
630 | Bondi to Bronte walking group to depart venue
630 | Breakfast opens
730 | Secretariat opens for presenters to check slideshows
800 | Final versions of presentations to be given to operator
800 | Check set up of conference room
845 | Ask staff still having breakfast to make their way to the Pavilion Ballrooms
830 | Secretariat opens
900 | Conference commences
Refer to agenda/pres sign off sheet
1045 | Morning tea
1100 | Conference resumes
Refer to agenda/pres sign off sheet
1230 | Lunch
1300 | Murder Mystery Character Notes to be handed out to anyone who didn't get a copy during registration
1300 | Ensure room is split, presentations changed on screen
1300 | Ensure Laurie Macri's handouts are placed on the tables for Australian Breakout Session at 1515
1415 | Australian/Asian breakout sessions commence
Refer to agenda/pres sign off sheet
1500 | Sweet Art to set up decorations for dinner |  |  |  | Anthea | TBC
1545 | Afternoon tea
1545 | Ensure room is reopened, presentations changed on screen
1600 | Conference resumes
Refer to agenda/pres sign off sheet
1700 | Conference concludes
1630 | Check set up of dinner, poster etc
Dinner Timing Schedule
1900 | Pre-dinner drinks
1930 | Make announcement: "guests to be seated" |  |  |  |  | TBC
1935 | Murder Mystery to commence |  |  |  | Anisha
1945 | Buffet to open
2105 | Dessert to be served
2235 | Muder Mystery to conclude
2400 | Event concludes
Thursday 25 September 2008
Time | Task |  |  |  | Key Contact | Contact Number
600 | Breakfast opens
645 | Ask staff still having breakfast to make their way to the Pavilion Ballrooms
700 | Coach departs for:

## Mountain Heritage - Blue Mtns (hidden)
Conference Option 6: Mountain Heritage Hotel & Spa Retreat - Blue Mountains
NB: This venue does not have enough rooms to accommodate our group
|  | 1st Day | 2nd Day
Accomodation B&B
Day Conference Package
includes lunch
Dinner
Drink Packages
Activity?
Themed night?
Total |  |  | 0
Website: | http://www.mountainheritage.com.au/
Image Gallery
Facts & Figures
Location: | Cnr Apex & Lovel Streets, Katoomba
Distance from Sydney: | 90 minutes drive
Conference Room Max Cap: | 80 Classroom Style
Number of Breakout Rooms: | 3 Other Meeting Rooms
Number of Single Bedrooms: | TBC
Number of Executive Suites: | TBC
Number of Shared Bedrooms: | TBC
Number of Restaurants: | 1 - Jamison Views Room
Other Comments: | 42 rooms available including 4 suites
Score out of 10: | 5

## Venue Comparison
Venue Comparison
| Option 1 | Option 2 | Option 3 | Option 4 | Option 5 | Option 6 | Option 7 | Option 8
Hotel
Approx Total
Ranking
Recommendation | bar: Venue Comparison Option 1 to Venue Comparison Option 7
Next Steps | bar: Venue Comparison Option 1 to Venue Comparison Option 7